## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project (Log Analytics Monitoring Engine) and milestone planning | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S2 | S2 | US-001 | Understanding Python, Libraries, API, Backend, Frontend, Web Technologies, Dask, Config Files | MUST HAVE | Python Official Docs | Gogula Avinash Kumar | 3- Completed
S3 | S3 | US-001 | Dask Basics, Cluster Setup, Data Manipulation, Virtual Environment | MUST HAVE | Dask Documentation | Gogula Avinash Kumar | 3- Completed
S4 | S4 | US-001 | Skillr Website Overview & Virtual Environment Management | SHOULD HAVE | Skillr Platform, Python venv Docs | Gogula Avinash Kumar | 3- Completed
S5 | S5 | US-001 | Installing Dask (pip install dask[complete]) | MUST HAVE | Python | Gogula Avinash Kumar | 3- Completed
S6 | S6 | US-001 | Creating main and dask config & Connecting to Dask | MUST HAVE | Dask Setup | Gogula Avinash Kumar | 3- Completed
S7 | S7 | US-001 | Creating Log Schema (schema design & parser concept) | MUST HAVE | Python, Project Requirement | Gogula Avinash Kumar | 3- Completed
S8 | S8 | US-001 | Developing parser & Regex Implementation | MUST HAVE | Python re Module Docs | Gogula Avinash Kumar | 3- Completed
S9 | S9 | US-001 | Explained parser code, regex, and timestamp conversion. | MUST HAVE | Python Documentation | Gogula Avinash Kumar | 3- Completed
S10 | S10 | US-001 | Milestone 1 Completion | MUST HAVE | Completion of Days 1–9 Tasks | Gogula Avinash Kumar | 3- Completed
S11 | S11 | US-001 | Introduction to Python Ray | SHOULD HAVE | Ray Documentation | Gogula Avinash Kumar | 3- Completed
S12 | S12 | US-001 | Project Review & Feedback Collection | MUST HAVE | Milestone 1 Deliverables | Gogula Avinash Kumar | 3- Completed
S13 | S13 | US-001 | Milestone 2 Planning & Review Discussion | MUST HAVE | Milestone 1 Completion | Gogula Avinash Kumar | 3- Completed
S14 | S14 | US-001 | Updating Milestone 1 and Creating Data Pipeline to Convert Logs into Dask Bag | MUST HAVE | Dask Configuration & Parser Implementation | Gogula Avinash Kumar | 3- Completed
S15 | S15 | US-001 | Explained Log Injection & Distributed Processing | MUST HAVE | python Documentation | Gogula Avinash Kumar | 3- Completed
S16 | S16 | US-001 | Explain Start and end time is understanding the dask | SHOULD HAVE | Dask Configuration & Parser Implementation | Gogula Avinash Kumar | 3- Completed
S17 | S17 | US-001 | Explain briefly about milestone-3 | MUST HAVE | Streamlit for dashboard UI | Gogula Avinash Kumar | 3- Completed
S18 | S18 | US-001 | Explain Anamoly detection and send alert messages | MUST HAVE | Pandas for log analysis, and SMTP | Gogula Avinash Kumar | 3- Completed
S19 | S19 | US-001 | Explain Z-Score and How it works | MUST HAVE | NumPy for Z-score calculation | Gogula Avinash Kumar | 3- Completed
S20 | S20 | US-001 | Create the Detection.py to calculate Z-Score | MUST HAVE | Pandas, NumPy | Gogula Avinash Kumar | 3- Completed
S21 | S21 | US-001 | Explain threshold value,error count based on minute and time stamp and absolute value | SHOULD HAVE | NumPy | Gogula Avinash Kumar | 3- Completed
S22 | S22 | US-001 | Explain Final project ppt and how to explain it | MUST HAVE | Python Documentation | Gogula Avinash Kumar | 3- Completed
S23 | S23 | US-001 | Create Log data and Pipeline converts to dataframe | MUST HAVE | Dask, Pandas | Gogula Avinash Kumar | 3- Completed
S24 | S24 | US-001 | Create the Duplicate log data and generate log data | MUST HAVE | Python Faker | Gogula Avinash Kumar | 3- Completed
S25 | S25 | US-001 | Introduction to the Stremlit Dashboard | SHOULD HAVE | Streamlit Framework | Gogula Avinash Kumar | 3- Completed
S26 | S26 | US-001 | How it work on Browser in Streamlit | MUST HAVE | Web Browser | Gogula Avinash Kumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7